## Overall_Update (hidden)
| Project | Owner | Resoure | status | Comments | Fedback
1 | JAGS | Satya | Satya (React website design - dynamic) | Payment integration frontend - over; backend connection yet to start and STEEL WEBSITE(Payment integration, Add to Cart - frontend completed; backend yet to start) | Frontend fully integrated successfully. Developer needs product addtional information. | Ensure secure payment integration for both client and customer ends.
2 | JCS | Susi, Ruban | Susi, Ruban (React website design - static) | The entire static website has been completed. | A chatbot has also been added to the company website as per the client’s requirements. | Build a Home page and Products page for JCS control panel
3 | Saffron | Sanjay | Sanjay (React e-commerce website - dynamic) | HTML and CSS to React conversion (entire pages) | Footer color need to change for the website | Payment integration security for client and customer using React framework.
4 | Coins Software | Assign (Frontend & Backend Developers) | Backend support - Vinay; Frontend - Susi, Ruban, Satya | Requirements need to the cliend end | Requirements need to the cliend end | Requirements need to the cliend end
5 | Product 1 | Ruban, Susi, (Company product design) | Susi-(Payroll system, EMS) and Ruban-(Attendance management System) | ● Completed (all the above given comments/feedbacks) ● Admin pages like dashboard and other access-related components are completed. ● Backend development work will now be initiated.Developed a login page for Ceitcs, and created a comprehensive dashboard for attendance management. Implemented features to display the employee list, categorized into permanent, contract, and internship roles. Integrated attendance tracking, leave and holiday management pages, along with a workdays module. Designed attendance and individual attendance report functionalities. | EMS: • Document verification for passport, certifications, etc. • Offer & joining letter templates drafted | Payroll System: • Section for onsite employees added • Currency change handling completed EMS: • Document verification for passport, certifications, etc. • Offer & joining letter templates drafted.Build a about and contact Attendance Management System: Built a login page for Ceitcs and created a dashboard to manage attendance effectively. Implemented an employee listing feature that categorizes staff as permanent, contract, or internship, along with attendance tracking. Made updates to the holidays page and added new columns to the leave page, including support for paternity and maternity leave.
5a | Mobile development | Moni(react native) | moni(company app) | ●Learned React Native including environment setup, Expo, and core/native components. Completed a sample project and also worked on a React Native project in collaboration | Learning Curvey | Learning Curvey and side by yet to start mobile app integration
6 | Code Converter | Vinay, Satya | Vinay, (Backend scripts); Satya (Frontend design) | The process of fetching from frontend to backend for this product has been completed. | Additionally, the script needs to be modified to include explanations for both input and output during code conversion, as fetching is still in progress. | The frontend-to-backend integration has been completed with a clear explanation for both input and output. The analysis prompt file was successfully created.
6a | code converter with cloud AI | Vishal | Vishal(Cloud API) | API handling in the code converter and Implemented API handling and integrated the analysis prompt feature in the code converter | Analysis prompt should be the file format | Explanation should be add for both input and output with the help of python Script
7 | CVS | Assign (Susi and Ruban) | Susi and Ruban | Yet to start | Yet to start | yet to start
8 | LSEG | Assign (Frontend & Backend Developers) | Frontend developer and backend developer (To be assigned) | Resumes has sent to the client company | processing | processing
9 | Mechanical Projects | Assign(frontend developer and backend developer) | Screening process | Screening process | Screening process | Yet to start
10 | company website and security | Vincy | Vincy(react website design and Security for the wesite | The Ceitcs company website has been successfully completed using the React framework, and the career page is functional. | The career page is being updated with new features. | Yet to be deployed in our workspace.
11 | Options-wheels-strategy | Vincy,Vinay | Vincy, Vinay (Entire code analyzing) | Waiting to out clinet meeting | Yet to start | Yet to start

## Dashboard
| Project | Owner | Resoure | status | Comments | Fedback | Overall_percentage | Target_date | Reviewed_By
1 | Home Services Application | Lokesh | frontend-DART , Backend-Node js,Database-Mongo DB | 🔄 In Progress | The project is currently in progress. Approximately 50% of the frontend development and 50% of the backend development have been completed. The remaining features, integrations, testing, and optimizations are under development |  | 50% | 2026-07-10
2 | Employee Management System | Vinay and Kavin | Frontend-React, Backend Python ,Backend-SQL SERVER | 🔄 In Progress | The frontend and backend development have been completed successfully. The application is now ready for deployment. The next steps are to provision the production database, configure the hosting environment, and deploy the application to production. |  | 90% | 2026-06-20 | Malar mam
3 | Price Comparation | Janarthan and Rishikesh | Frontend-React, Backend Python ,Database-Mongo DB | 🔄 In Progress | The project has achieved a 70% completion status, successfully deploying a thread-safe multi-user scraper framework capable of handling concurrent client lookups simultaneously. Additionally, the dual database configurations have been verified, matching automated tokenized checks against the persistent MongoDB storage layers seamlessly. |  | 70% | 2026-06-22
4 | ATTENDANCE MANAGEMENT SYSTEM AND PAYROLL MANAGEMENT SYSTEM | Naveen Kumar | Frontend-React, Backend-Node.js ,Database-SQL Server | 🔄 In Progress | ATTENDANCE MANAGEMENT SYSTEM: Completed Employee Management, Leave Management, Holiday Management, Working Days, Employee Profile,Notification Badge, Dashboard Enhancements, SQL Server Integration, and GitHub Setup. Currently working on Leave Dashboard Statistics synchronization to ensure approved leave counts and leave balance are updated accurately across all dashboard modules. Final testing, bug fixes, and performance optimization are in progress. PAYROLL MANAGEMENT SYSTEM : Resolved major SQL Server database issues, data integrity problems, and backend integration challenges across the Payroll Management System. Currently working on UI/UX improvements, form design enhancements, layout alignment fixes, responsive behavior, and overall user experience optimization across Admin and Employee modules. |  | 90% | 2026-06-08 | Malar mam
5 | Online Tuition App (Android & iOS) | Manoj Kumar | Frontend-DART, Backend-Node.js ,Database-Mongo DB | 🔄 In Progress | Project is currently 85% completed with core modules such as Home Page, Subjects, Tutor Listing, and Admin Login fully implemented. Pending work includes Student Login, Teacher Login, Attendance Management, Payment Gateway Integration, and Search enhancements. Testing, bug fixing, and performance optimization are currently in progress. Final tasks include Android & iOS build generation, deployment, and production release |  | 85% | 2026-07-10

## PRICE COMPARATION
PRICE COMPARATION
S.No | Owner Of Task | Module | Page/Feature | Progress % | Tasks | Status | Target | Pending_Task | Reviewed_By
1 | Janarthanan | Environment | Git Repo Initialization | 100% | Initialized Git tracking workspace for baseline files. | Completed |  | None
2 | Janarthanan | Environment | .gitignore Setup | 100% | Configured exclusion rules for __pycache__ and runtime logs. | Completed |  | None
3 | Janarthanan & Rishi | Research | SerpAPI Engine Evaluation | 100% | Conducted architectural analysis on Google Shopping integrations. | Completed |  | None
4 | Janarthanan & Rishi | Research | SerpAPI Deprecation Root Cause | 100% | Failed/Deprecated. Tracked structural query blocks and rate errors. | Dropped |  | None
5 | Janarthanan & Rishi | Research | Playwright Browser Selection | 100% | Verified automated page-routing via headless chromium context. | Completed |  | None
6 | Janarthanan | Backend | Playwright Engine Hooks | 100% | Initialized launch hooks and runtime instance handlers. | Completed |  | None
7 | Janarthanan | Backend | Amazon India Parser Rules | 100% | Configured HTML element mapping for real-time item cards. | Completed |  | None
8 | Janarthanan | Backend | Flipkart India Parser Rules | 100% | Configured class tag selectors for real-time item grids. | Completed |  | None
9 | Janarthanan | Backend | HTTP Custom Header Payload | 100% | Inserted language flags and customized request headers. | Completed |  | None
10 | Janarthanan | Backend | User-Agent Rotation Engine | 100% | Configured masked browser browser identity cycling strings. | Completed |  | None
11 | Janarthanan | Backend | Signature Detection Bypass | 100% | Disabled explicit AutomationControlled browser properties. | Completed |  | None
12 | Janarthanan | Backend & DB | Multi-User Async Spawner | 100% | Integrated concurrent coroutine workers safely. | Completed |  | None
13 | Janarthanan | Backend & DB | Platform Request Concurrency | 100% | Wrapped Amazon/Flipkart fetch steps using asyncio.gather. | Completed |  | None
14 | Janarthanan & Rishi | Backend & DB | MongoDB Instance Provisioning | 100% | Configured local database engine hosting profiles. | Completed |  | None
15 | Janarthanan | Backend & DB | Absolute upsert Scripting | 100% | Built collection write logic using indexing keys. | Completed |  | None
16 | Janarthanan | Backend & DB | Fallback Verification Hook | 100% | Deployed $and regex fallback lookup loops. | Completed |  | None
17 | Janarthanan | Backend & DB | Lifespan Auto-Flush System | 40% | Building FastAPI lifecycle timer thread loop routines. | In Progress | 2026-06-22 | Fix interval loop drop
18 | Janarthanan | Backend | Text Normalization & Lowercase | 100% | Sanitizes input search query strings automatically. | Completed |  | None
19 | Janarthanan | Backend | Compound Dimension Tokenizer | 100% | Splits structural dimensions inline (e.g., 128gb -> 128, gb). | Completed |  | None
20 | Janarthanan | Backend | Title Accessory Exclusions | 100% | Filters out accessory pollution (cases, chargers, skins). | Completed |  | None
21 | Janarthanan | Backend | Cross-Model Leakage Blocker | 100% | Restricts mixed item variants (Plus/Max editions). | Completed |  | None
22 | Janarthanan | Backend | Price Stripper Sanitizer | 100% | Extracts numeric values using price regex filter [^\d]. | Completed |  | None
23 | Janarthanan | Backend | Array Low-to-High Sorter | 100% | Orders results systematically by price ascending. | Completed |  | None
24 | Janarthanan | Backend & DB | FastAPI Endpoint Routing | 100% | Deployed active /search?q= route endpoint on port 8000. | Completed |  | None
25 | Janarthanan & Rishi | Backend & DB | CORS Policy Configuration | 100% | Set allowance headers enabling client script calls. | Completed |  | None
26 | Rishi | Frontend | Streamlit UI Framework Proof | 100% | Verified raw connectivity routing inside app.py. | Completed |  | None
27 | Rishi | Frontend | HTML5/JS Workspace Migration | 100% | Swapped out Streamlit interface file with index.html. | Completed |  | None
28 | Rishi | Frontend | Grid Layout CSS Design | 100% | Established clean layout container stylings. | Completed |  | None
29 | Rishi | Frontend | Typographic & Token Theme | 100% | Applied Syne & DM Sans system fonts with dark mode token. | Completed |  | None
30 | Rishi | Frontend | Responsive Category Navigation | 100% | Added dynamic selector tabs for All, Mobile, and Laptops. | Completed |  | None
31 | Rishi | Frontend | Inline Placeholder Modifier | 100% | Alters field text matching selected item categories. | Completed |  | None
32 | Rishi | Frontend | Client Async Fetch Call | 100% | Wired Javascript search functions to port 8000. | Completed |  | None
33 | Rishi | Frontend | Loading Shimmer Animation | 100% | Implemented custom card skeletons for smooth visual delays. | Completed |  | None
34 | Rishi | Frontend | Real-Time Status Engine Dot | 100% | Added indicator color codes reflecting live/cached hits. | Completed |  | None
35 | Rishi | Frontend | Dynamic Low Price Indicator | 100% | Renders absolute lowest-deal center panel alert bar. | Completed |  | None
36 | Rishi | Frontend | Cards Render Image Fallback | 100% | Configured onerror placeholder swaps for missing images. | Completed |  | None
37 | Janarthanan | Backend & DB | Concurrent Multi-User Load Test | 60% | Simulating several parallel connections against search endpoints. | In Progress | 2026-06-21 | Complete stress loop
38 | Janarthanan | Backend & DB | DB Verification Multi Check | 80% | Verifying data validity against active cache collections. | In Progress | 2026-06-21 | Cross check indexing
39 | Janarthanan | Backend | Product Leak Boundary Review | 50% | Evaluating filtering tolerances on miscellaneous keywords. | In Progress | 2026-06-11 | Optimize regex maps
40 | Rishi | Frontend | Live Search Suggestions | 20% | Dropdown overlay shell created; awaiting connection to keypress matching logic. | In Progress | 2026-06-12 | Link input listener to database query logic
41 | Rishi | Frontend | Product Alignment Fixes | 45% | Fixing height variances on long titles to keep text/buttons aligned. | In Progress | 2026-06-13 | Apply flexbox-column stretch rules to .p-card

## Home Services Application
Home Services Application
S.No | Owner of this Task | Module | Page/Feature | Progress % | Tasks | Status | Target | Pending_task | Reviewed_By
| Owner | Module | Page/Feature |  | Remarks
1 | Lokesh | Authentication | User Login | 100% | OTP Login Working | Completed
2 | Lokesh | Authentication | Partner Login | 100% | Login API Connected | Completed
3 | Lokesh | Authentication | Owner Login | 100% | Dashboard Access Working | Completed
4 | Lokesh | User App | Categories | 100% | Working | Completed
5 | Lokesh | User App | Service Details | 100% | Booking Button Added | Completed
6 | Lokesh | Partner App | Partner Registration | 100% | Registration Working | Completed
7 | Lokesh | Owner App | Owner Dashboard | 100% | Working | Completed
8 | Lokesh | Backend | Authentication APIs | 100% | Working | Completed
9 | Lokesh | User App | Home Page | 90% | Search Improvements Pending | In Progress | 2026-06-12
10 | Lokesh | User App | Service Listing | 90% | UI Improvements Done | In Progress | 2026-06-12
11 | Lokesh | Backend | User APIs | 90% | Minor Fixes Pending | In Progress | 2026-06-12
12 | Lokesh | User App | Booking Page | 85% | Validation Pending | In Progress | 2026-06-30
13 | Lokesh | User App | Profile Page | 80% | Edit Profile Pending | In Progress | 2026-06-30
14 | Lokesh | Owner App | User Management | 80% | Improvements Pending | In Progress | 2026-06-30
15 | Lokesh | Backend | Booking APIs | 75% | History API Fix Needed | In Progress | 2026-06-30
16 | Lokesh | User App | Booking History | 70% | JSON Error Fix Pending | In Progress | 2026-06-30
17 | Lokesh | Partner App | Approval Request | 70% | Owner Approval Flow Under Development | In Progress | 2026-07-07
18 | Lokesh | Partner App | Partner Dashboard | 70% | Service Management Pending | In Progress | 2026-07-07
19 | Lokesh | Owner App | Partner Approval Management | 70% | Approve/Reject Workflow Under Development | In Progress | 2026-07-09
20 | Lokesh | Backend | Partner APIs | 70% | Approval Flow Development Ongoing | In Progress | 2026-07-09
21 | Lokesh | Owner App | Service Management | 60% | CRUD Pending | In Progress | 2026-07-10
22 | Lokesh | User App | Chat Page | 40% | Real Chat Not Implemented | In Progress | 2026-07-10

## CeiTCS_Professional_academy
CeiTCS_Professional_academy
S.No | Owner of this Task | Module | Page/Feature | Progress % | Tasks | Status | Target | Pending Task | Reviewed_By
1 | Kevin | Admin | Employee Page | 100% | Added Back Button Navigation | Completed | 2026-06-12 | -
2 | Rishi | participant | Employee Registration | 100% | Fixed Phone Number Validation | Completed | 2026-06-12 | -
3 | Jana | participant | Employee Registration | 100% | Fixed Email Validation | Completed | 2026-06-12 | -
4 | Jana | Faculty | Document Upload | 100% | Made Document Upload Mandatory | Completed | 2026-06-12 | -
5 | Rishi | Participant,Faculty | Profile Page | 100% | Added Participant Profile View | Completed | 2026-06-12 | -
6 | Rishi | Participant | Profile Edit Page | 100% | Added Participant Profile Edit Functionality | Completed | 2026-06-12 | -
7 | Kavin | Dashboard | All Login Modules | 100% | Implemented Dashboard Button | Completed | 2026-06-12 | -
8 | Jana | UI Validation | Forms | 100% | Added Field Length Validations | Completed | 2026-06-12 | -
9 | Jana | Authentication | Forgot Password | 100% | Implemented Forgot Password for Participant & Admin Login | Completed | 2026-06-12 | -
10 | Rishi | UI | Overall Application | 90% | UI Setup and Alignment Fixes | Completed | 2026-06-12
11 | Kevin | Feedback | Reject Feedback Status | 100% | Reject Feedback Status Implementation for both faculty and participant | completed | 2026-06-16 | Status update logic pending | Rajini sir
12 | Kevin | Admin | User Actions | 100% | Replace Delete with Activate/Deactivate | completed | 2026-06-16 | Activate/Deactivate functionality pending | Rajani sir
13 | Jana | participant | User Actions | 100% | Phone number country code fixed | completed | 2026-06-16 | Phone number country code pending | Rajani sir
14 | kevin | faculty | UI Actions | 100% | Subject dropdown button to the participantend | completed | 2026-06-18 | Subject dropdown button to the participantend | Rajini sir
15 | Kevin | participant | UI Actions | 100% | Query page Ui has changed | Improgress | 2026-06-16 | Instead of traniee need facultyQuerie UI has pending | Rajini sir
16 | Rishi,Jana | faculty,participant | Payement Action | 0% | Need to disscuss with the management | Improgress | based on the management requirement will fix the target date | payment receipt preview
17 | Rishi | faculty,participant | Payement Action | 0% | Need to disscuss with the management | Improgress | based on the management requirement will fix the target date | payment Integration
18 | Kevin | Admin---faculty,participant | Faculy Action | 90% | integration has fixed between facuty and participant with the help of course Id | Improgress | 2026-06-22 | faculty participant connect
19 | Unassigned | Testing | Faculty & Participant Module | 0% | Test Faculty and Participant functionalities with initial 5 members | Improgress | Yet to plan | Functional testing, validation testing, and bug verification pending
20 | Jana | Faculty | faculty module | 100% | Faculty functionality implmented the schedule data | completed | 2026-06-16
21 | Rishi | UI Validation | Course module | 100% | Course and dashboard Ui changed | Completed | 2026-06-16 | Course and dashboard Ui change pending
23 | Rishi | data Management | data module | 100% | Mentors page delete old date and as per management need to pull the new data | Completed | 2026-06-16 | Mentors page delete old date and as per management need to pull the new data pending
24 | Jana,Rishi | faculty,participant | Notification module | 100% | Notification flow done | completed | 2026-06-19 | Notification flow pending
25 | jana | Participant | data module | 100% | Mail trigger once scheduled the class | completed | 2026-06-19 | Mail trigger once scheduled the class | Rajini sir
26 | jana | faculty | data module | 100% | Standard UI Alignment pending for schedule the classes completed | completed | 2026-06-22 | Standard UI Alignment pending for schedule the classes
26 | kevin | faculty | certificate module | 100% | Experience certificate and external certificate and Training Certificate Anyone is manditory completed | completed | 2026-06-22 | Experience certificate and external certificate and Training Certificate Anyone is manditory
27 | kevin.jana | fuculty-admin | integration | 90% | integration has fixed between admin and faculty with the help of course Id | completed | 2026-06-22
28 | kevin,rishi | participant-admin | integration | 80% | Integration has fixed | Improgress | 2026-06-23 | Integration has been working participant and admin pending
29 | Rishi | Participant | Attendence module | 0% | Attendance need to complete for participant | Improgress | 2026-06-25 | Attendance need to complete for participant is pending
30 | Jana | faculty | Assignment module | 0% | Assignments module implement for between faculty and participant | Improgress | 2026-06-26 | Assignments module implement for between faculty and participant is pending
31 | kevin | Admin | Notification module | 0% | System Alert | Improgress | 2026-06-27 | System Alert is pending
32 | unassigned | Faculty | UI | 0% |  | Improgress | yet not plan | faculty page need the profile dashboard view,log out pending
33 | Rishi | Admin | Ui | 100% | New course has added in the dashboard | Completed | 2026-06-26 | new course need to add pending
34 | Rishi | admin | UI | 100% | new field from the faculty page (From date,upload button) completed | completed | 2026-06-26 | new field from the faculty page (From date,upload button)
35 | Rishi | Faculty | UI | 50% |  | Improgress |  | Faculty to participant assignment
36 | Rishi | Participant | UI | 50% |  | improgress |  | Action buttons need to work pending flow like reject,deactivate,activate
37 |  | Dashboard | frontend-Ui | 50% |  | improgress |  | Ui-alignment dashboard is pending
38 |  | participant | frontend-Ui | 50% |  | Improgress |  | Paticipant and faculty that manditory Icons pending

## EMPLOYEE MANGEMENT SYSTEM
EMPLOYEE MANGEMENT SYSTEM
S.No | Owner Of Task | Module | Page/Feature | Progress % | Tasks | Status | Target | Pending_Task | Reviewed By
1 | Vinay | Authentication | Super Admin Login | 100% | Working | Completed | - | - | Malar Mam
2 | Vinay | Authentication | Super Admin Registration | 100% | Working | Completed | - | - | Malar Mam
3 | Vinay | Authentication | Admin Login | 100% | Working | Completed | - | - | Malar Mam
4 | Vinay | Authentication | Employee Login | 100% | Working | Completed | - | - | Malar Mam
5 | Vinay | Employee Portal | Profile Completion | 100% | Working | Completed | - | - | Malar Mam
6 | Kavin | Employee Portal | Employee Dashboard | 100% | Working | Completed | - | - | Malar Mam
7 | Kavin | Employee Portal | Employee Profile | 100% | Working | Completed | - | - | Malar Mam
8 | Kavin | Employee Portal | Employee Layout | 100% | Working | Completed | - | - | Malar Mam
9 | Vinay | Document Management | Document Upload & Verification | 100% | Working | Completed | - | - | Malar Mam
10 | Vinay | Employee Management | Add Employee | 100% | Working | Completed | - | - | Malar Mam
11 | Kavin | Employee Management | Employee List | 100% | Working | Completed | - | - | Malar Mam
12 | Kavin | Employee Management | Employee Profile Review | 100% | Working | Completed | - | - | Malar Mam
13 | Kavin | Communication | Email Communication | 100% | Working | Completed | - | - | Malar Mam
14 | Kavin | Communication | Mail History & Details | 100% | Working | Completed | - | - | Malar Mam
15 | Vinay | Worker Management | Add Worker | 100% | Working | Completed | - | - | Malar Mam
16 | Kavin | Worker Management | Workers Directory | 100% | Working | Completed | - | - | Malar Mam
17 | Kavin | Worker Management | Worker Offer Letter | 100% | Working | Completed | - | - | Malar Mam
18 | Kavin | Admin Dashboard | Sidebar | 100% | Working | Completed | - | - | Malar Mam
19 | Kavin | Admin Dashboard | Topbar & Notifications | 100% | Working | Completed | - | - | Malar Mam
20 | Kavin | Admin Dashboard | Dashboard Analytics | 100% | Working | Completed | - | - | Malar Mam
21 | Vinay | Database | Local SQL Server | 100% | Connected Successfully | In Progress | 2026-06-15 | Hosting Pending
22 | Kavin | UI/UX | Frontend CSS for All Pages | 100% | Completed | Completed | - | -
23 | Vinay and Kavin | Testing | System Testing | 80% | Ongoing | In Progress | 2026-06-10 | Complete Testing
24 |  | Deployment | Production Deployment | 0% | Not Started | Pending | 2026-06-20 | Deployment Pending
feeback button while rejecting the document
UI need to change documents look like Emplyee_documents and Employee_communication
temporary_Access work flow

## PRICE COMPARATION(Backend) (hidden)
Price Scope
S.No | Developer | Module / Page / Feature | Status | Progress % | Remarks
1 | Rishikesh | React Project Setup & Folder Structure | ✅ Completed | 100 | Created project architecture with components, pages, hooks, services, and context folders
2 | Rishikesh | Home Page Development | ✅ Completed | 100 | Developed main landing page with product search functionality
3 | Rishikesh | Navigation Bar | ✅ Completed | 100 | Implemented responsive navigation and branding section
4 | Rishikesh | Search Module | ✅ Completed | 100 | Developed search interface and integrated search input functionality
5 | Rishikesh | API Integration | ✅ Completed | 100 | Connected frontend with FastAPI backend APIs
6 | Rishikesh | Search State Management | ✅ Completed | 100 | Implemented custom React hooks for search operations
7 | Rishikesh | Product Listing Cards | ✅ Completed | 100 | Developed dynamic product display cards
8 | Rishikesh | Price Comparison Dashboard | ✅ Completed | 100 | Displayed Lowest, Highest, Average Price and Savings information
9 | Rishikesh | Best Deal Recommendation | ✅ Completed | 100 | Highlighted lowest-price product with Best Deal badge
10 | Rishikesh | Sorting Functionality | ✅ Completed | 100 | Added sorting by Relevance, Price Low-High, High-Low, and Name
11 | Rishikesh | Marketplace Filter | ✅ Completed | 100 | Implemented Amazon and Flipkart filtering options
12 | Rishikesh | Loading Skeleton UI | ✅ Completed | 100 | Added shimmer loading effects during API calls
13 | Rishikesh | Error Handling Module | ✅ Completed | 100 | Implemented error messages and retry functionality
14 | Rishikesh | Theme Management | ✅ Completed | 100 | Added Dark/Light mode using React Context API
15 | Rishikesh | Responsive UI Development | ✅ Completed | 100 | Optimized UI for Desktop, Tablet, and Mobile devices
17 | Rishikesh | Glassmorphism UI Design | ✅ Completed | 100 | Implemented modern glassmorphism design and visual effects
18 | Rishikesh | Frontend Testing & Bug Fixes | 🔄 In Progress | 95 | Performed UI testing and resolved frontend issues
19 | Rishikesh | Backend Connectivity Validation | 🔄 In Progress | 95 | Verified API integration and data flow between frontend and backend
20 | Rishikesh | Documentation & README Preparation | ✅ Completed | 100 | Created project setup guide and documentation

## AMS and PMS
ATTENDANCE MANAGEMENT SYSTEM AND PAYROLL MANAGEMENT SYSTEM
S.No | Owner Of Task | Module | Page/Feature | Progress % | Tasks | Status | Target | Pending_Task | Reviewed By
1 | Naveen Kumar | AMS Authentication | Admin Login | 100% | Working Successfully | Completed | - | - | Malar Mam
2 | Naveen Kumar | AMS Authentication | Employee Login & Signup | 100% | Authentication Working | Completed | - | - | Malar Mam
3 | Naveen Kumar | AMS Employee Portal | Employee Dashboard | 100% | Dashboard Working | Completed | - | - | Malar Mam
4 | Naveen Kumar | AMS Employee Portal | Employee Profile | 100% | Profile Management Working | Completed | - | - | Malar Mam
5 | Naveen Kumar | AMS Leave Management | Leave Application | 100% | Apply Leave Functionality Working | Completed | - | - | Malar Mam
6 | Naveen Kumar | AMS Leave Management | Leave Approval & Rejection | 100% | Admin Workflow Working | Completed | - | - | Malar Mam
7 | Naveen Kumar | AMS Leave Management | Leave Notification Badge | 100% | Employee Leave Alerts Added | Completed | 2026-05-29 | - | Malar Mam
8 | Naveen Kumar | AMS Management | Holiday Management | 100% | Working Successfully | Completed | - | - | Malar Mam
9 | Naveen Kumar | AMS Management | Working Days Module | 100% | Working Successfully | Completed | - | - | Malar Mam
10 | Naveen Kumar | AMS Database | SQL Server Integration | 100% | Database Migration Completed | Completed | - | - | Malar Mam
11 | Naveen Kumar | AMS Dashboard | Leave Dashboard Statistics | 100% | Leave Count Synchronization Ongoing | Completed | 2026-06-05 | -
12 | Naveen Kumar | Testing | AMS Testing | 100% | Final Validation Ongoing | Completed | 2026-06-05 | -
13 | Naveen Kumar | PMS Dashboard | Payroll Dashboard UI Improvements | 100% | UI Enhancements Ongoing | Completed | 2026-06-08 | Minor UI Fixes
14 | Naveen Kumar | PMS Database | SQL Server Optimization | 100% | Query Optimization Completed | Completed | - | -
15 | Naveen Kumar | PMS Database | Data Integrity & Consistency Fixes | 100% | Database Issues Resolved | Completed | - | -
16 | Naveen Kumar | Source Control | GitHub Repository Setup | 100% | Repository Configured Successfully | Completed | - | -
17 | Naveen Kumar | PMS Management | Admin removes Leave Apporvals | 100% | remove full Leave Approvals | Completed | 2026-06-17
18 | Naveen Kumar | PMS Management | Employee Apply leave Removing | 100% | Apply Leave Functionality remove | Completed | 2026-06-18
19 | Naveen Kumar | AMS Testing | AMS Load Testing | 75% | Data and uesr load testing | Inprogress
20 | Naveen Kumar | PMS Dashboard | Admin Dashboard | 30% | Department Count | Inprogress | 2026-06-23
21 | Naveen Kumar | PMS Department | Monthly Payroll Page | 0% | Department Name is wrong | Inprogress | 2026-06-25
22 | Naveen Kumar | PMS Department Update | Database Update | 0% | Department Table is not Loading EMP ID | Inprogress | 26-06-2026

## Online Tuition App (Android & i
ONLINE TUITION APP FOR ANDROID & IOS
S.No | Owner | Module | Page/Feature | Progress % | Tasks | Status | Pending Task | Target | Reviewed By
1 | Manoj | Project Setup | Flutter Project Configuration | 100% | Project Setup Completed | Completed | -
2 | Manoj | React Conversion | React UI to Flutter Conversion | 100% | Conversion Completed | Completed | -
3 | Manoj | Home Page | Hero Banner & Slider | 100% | UI Completed | Completed | -
4 | Manoj | Home Page | Search Box & Navigation | 100% | Navigation Working | Completed | -
5 | Manoj | Home Page | Section Redirects | 100% | Redirects Working | Completed | -
6 | Manoj | Tutors Module | Tutor Listing & API Integration | 100% | Module Completed | Completed | -
7 | Manoj | Subjects Module | Subject Details Pages | 100% | Details Page Completed | Completed | -
8 | Manoj | Subjects Module | Subject Navigation & Routing | 100% | Routing Completed | Completed | -
9 | Manoj | Authentication | Admin Login | 100% | Login Working | Completed | -
10 | Manoj | Authentication | Student Login | 100% | Login Working | Completed | -
11 | Manoj | Authentication | Teacher Login | 100% | Login Working | Completed | -
12 | Manoj | Admin | Dashboard | 70% | Dashboard Development Ongoing | In Progress | UI & Statistics Integration | 2026-06-12
13 | Manoj | Admin | Student Dashboard | 50% | Student Module Working | In Progress | Dashboard Improvements | 2026-06-12
14 | Manoj | Admin | Teacher Dashboard | 50% | Teacher Module Working | In Progress | Dashboard Improvements | 2026-06-12
15 | Manoj | Attendance | Attendance Management | 60% | Attendance Module Working | In Progress | Attendance Enhancements | 2026-06-12
16 | Manoj | Payment | Payment Gateway Integration | 50% | Payment Module Development | In Progress | Payment API Integration | 2026-06-12
17 | Manoj | Search | Subject Search Functionality | 75% | Search Working | In Progress | Search Optimization | 2026-06-23
18 | Manoj | Subjects | Subject Management | 40% | Subject Module Under Development | In Progress | Subject CRUD & API Integration | 2026-06-26
19 | Manoj | Footer | Footer UI | 60% | UI Completed | In Progress | API Integration Pending | 2026-06-30
20 | Manoj | Backend | Authentication APIs | 80% | Login APIs Working | In Progress | Token Validation | 2026-06-30
21 | Manoj | Backend | Dashboard APIs | 40% | API Development Ongoing | In Progress | Complete Dashboard APIs | 2026-06-30
22 | Manoj | Testing | UI & Navigation Testing | 80% | Testing Ongoing | In Progress | Final Checking in UI | 2026-07-07
23 | Manoj | Explore More | Explore More Section | 10% | Not Started Yet | Pending | Complete UI & Content Integration | 2026-07-07
24 | Manoj | Deployment | Bug Fixing & Optimization | 30% | Pending | Pending | Fix Remaining Issues | 2026-07-10
25 | Manoj | Mobile App | Android & iOS App Development | 0% | Development Not Started | Pending | Start Mobile App Development | 2026-07-10
26 | Manoj | Testing | Android & iOS Device Testing | 0% | Testing Not Started | Pending | Verify App Run On Physical Devices | 2026-07-10

## Checksheet
Checksheet
Module | Status | Activity | Reviewed_by | pending | comments | Target_date
CeiTCS_Professional_academy_admin | Improgress | Development |  | System alert,Payment System
CeiTCS_Professional_academy_admin | Improgress | Testing |  | System alert,Payment System
CeiTCS_Professional_academy_admin | Improgress | coding |  | System alert,Payment System
CeiTCS_Professional_academy_admin | completed | Integration |  |  |  | 2026-06-24
CeiTCS_Professional_academy_admin | Improgress | Deployment
CeiTCS_Professional_academy_Faculty | Improgress | Development |  | Attendence,Assignment
CeiTCS_Professional_academy_Faculty | Improgress | Testing |  | Attendence,Assignment
CeiTCS_Professional_academy_Faculty | Improgress | coding |  | Attendence,Assignment
CeiTCS_Professional_academy_Faculty | completed | Integration |  | completed |  | 2026-06-24
CeiTCS_Professional_academy_Faculty | Improgress | Deployment
CeiTCS_Professional_academy_Participant | Improgress | Development |  | Assignment,Attendance,Payment
CeiTCS_Professional_academy_Participant | Improgress | Testing |  | Assignment,Attendance,Payment
CeiTCS_Professional_academy_Participant | Improgress | coding |  | Assignment,Attendance,Payment
CeiTCS_Professional_academy_Participant | Improgress | Integration |  | Assignment,Attendance,Payment |  | 2026-06-24
CeiTCS_Professional_academy_Participant | Improgress | Deployment |  | Assignment,Attendance,Payment

## Satya (hidden)
No | Task / Feedback | Status | Developer (Sathya) | Remarks / Next Steps | Other Enhancemennts
1 | Build static website for JAGS demo | ✅ Completed | Sathya | Static version completed and presented to client. | Basic layout and responsiveness
2 | Convert static site to dynamic after client demo | ✅ Completed | Sathya | Converted using React/Node.js (as applicable). | Connected to backend API
3 | Add product filter and dynamic features | ✅ Completed | Sathya | Filter functionality live on product page. | Sorting and search added
4 | Add chat box to homepage | ✅ Completed | Sathya | Chat feature integrated using third-party API. | Enhance the responsiveness and backend
5 | Set up email auto-reply | ✅ Completed | Sathya | Automated email responses configured via backend. | Used NodeMailer for replies
6 | Build dynamic JAGS Steel eCommerce site | ✅ Completed | Sathya | Demo shared with client for feedback. | Product showcase improved
7 | Enhance JAGS Steel added payment integration | ✅ Completed | Sathya | Basic integration (e.g., Razorpay) implemented. | Added test payment flow
8 | Add payment integration | ✅ Completed | Sathya | Basic integration (e.g., Razorpay) implemented. | Added test payment flow
9 | Improve payment integration (ongoing) | 🔄 In Progress | Sathya | Ongoing enhancements, expected to complete within Wed. | Adding secure checkout & wallet support
11 | Frontend developed for code converter | ✅ Completed | Sathya | Code Conversion Enhancements,Code & Explanation Separation | Output Format Enhancement

## Vincy (hidden)
No | Task / Feedback | Status | Developer | Remarks / Next Steps
1 | Home Page | ✅ Completed | Bearlin Wincy | Successfully developed and styled
2 | About us Page | ✅ Completed | Bearlin Wincy | Content and layout finalized
3 | feature Page | ✅ Completed | Bearlin Wincy | All features listed with design
4 | Blog Page | ✅ Completed | Bearlin Wincy | Blog section integrated
5 | Contact us Page | ✅ Completed | Bearlin Wincy | Form and contact details functional
6 | Services Page | ✅ Completed | Bearlin Wincy | All services displayed properly
7 | Experts Page | ✅ Completed | Bearlin Wincy | Team members showcased
8 | Careers Page | 🔄 In Progress | Bearlin Wincy | Under development, finalizing design

## Susi (hidden)
No | Task / Feedback | Status | Developer | Remarks / Next Steps
1 | JCS Control Panel Website: Build a Home page and Products page | ✅ Completed | Suseendiran | Successfully created Home page and Products page for JCS control panel website
2 | Payroll System: Add separate section for onsite employees with currency changes | ✅ Completed | Suseendiran | Successfully implemented dedicated section for onsite employees with currency management functionality
3 | EMS: Add document verification for passport | ✅ Completed | Suseendiran | Added passport to the document verification section
4 | EMS: Add document verification for course certifications | ✅ Completed | Suseendiran | Implemented course certifications in document verification section
5 | EMS: Create offer letter template | ✅ Completed | Suseendiran | Created initial template for offer letters
6 | EMS: Create joining letter template | ✅ Completed | Suseendiran | Developed basic joining letter template
7 | EMS: Backend development | 🔄 In Progress | Suseendiran | Started working on the backend implementation for the EMS system

## Ruban (hidden)
No | Task / Feedback | Status | Developer | Remarks / Next Steps
1 | Build a about and contact page for jcs control panel website | ✅ Completed | Ruban | Build a about and contact page for jcs control panel website
2 | build a login page for ceitcs | ✅ Completed | Ruban | build a login page for ceitcs
3 | create a dashboard for attendance | ✅ Completed | Ruban | create a dashboard for attendance
4 | the employes list permanent, contract, internship attendance | ✅ Completed | Ruban | the employes list permanent, contract, internship attendance
5 | leaves page and holidays page | ✅ Completed | Ruban | some changes in holidays page and also add a columns in leave page and update paternity and maternity leave
6 | workindays module | ✅ Completed | Ruban | workindays module
7 | attendance report | ✅ Completed | Ruban | Add a filter option in a weekly vise attendance report
8 | individual attendance report | 🔄 In Progress | Ruban | Create a individual attendance report
9 | learned react-native(environment setup,expo created , core and native components ) | ✅ Completed | Monika | a sample project in React Native
10 | React-native sample project | ✅ Completed | Monika | to work on ruban and susi project convert to react native
11 | React-native project(susi and Ruban project) | ✅ Completed | Monika

## Sanjay (hidden)
S.No | Page / Task | Status | Developer | Remarks
1 | Home page | ✅ Completed | Sanjay | Convert html to react js
2 | Product | 🔄 In Progress | Sanjay | Convert html to react js
3 | Contact | ✅ Completed | Sanjay | Convert html to react js
4 | Store | 🔄 In Progress | Sanjay | Convert html to react js and add Java script in the page
5 | payment Integration | 🔄 In Progress | Sanjay | Convert html to react js and java script in the page

## Vinay (hidden)
S. No. | Task / Feedback | Status | Developer(VinayKumar.S) | Remarks / Next Steps
1 | Create a GitHub account and store coding files in the GitHub repository. | ✅ Completed | Ceitcs Team | Repo created and code pushed.
2 | Automatically detect source language in Python script without manual input. | ⏳ In Progress | Developer | Language detection logic preparation
3 | Enable multiple file conversions and store results in GitHub repository. | ⏳ Planned This Week | Developer | sheduled to review the Script supports XML, JSON, Python.
4 | Refer to Replit for understanding AI performance (shared by client). | ✅ Reviewed | Developer | Replit reviewed during AI demo.
5 | Refer to Futurepedia for understanding AI performance (shared by client). | ✅ Reviewed | Developer | Futurepedia reviewed during AI demo.
6 | Create GitHub repo and connect script for multi-format conversion (XML, JSON, Python). | ✅ Completed | Developer | Script is connected to repo for conversions.
7 | Add company skill set to site: React, Python, Cloud, JS, Databases. | ✅ Completed | Web Admin | To be updated on the company site.
8 | Create sandbox and virtual machine to set up database. | ⏳ Planned This Week | Ceitcs Team | Scheduled setup for VM and sandbox.
9 | Develop workflows or business use cases for process streamlining. | ⏳ In Progress | Business Analyst | Use case documentation under preparation.