## EMS Project Tracker
S.No | Owner Of | Module | Page/Feature | Progress % | Remarks | Status | Target | Pending_Task | Reviewed By
1 | Vinay | Authentication | Super Admin Login | 100% | Working | Completed | - | - | Malar Mam
2 | Vinay | Authentication | Super Admin Registration | 100% | Working | Completed | - | - | Malar Mam
3 | Vinay | Authentication | Admin Login | 100% | Working | Completed | - | - | Malar Mam
4 | Vinay | Authentication | Employee Login | 100% | Working | Completed | - | - | Malar Mam
5 | Vinay | Employee Portal | Profile Completion | 100% | Working | Completed | - | - | Malar Mam
6 | Kavin | Employee Portal | Employee Dashboard | 100% | Working | Completed | - | - | Malar Mam
7 | Kavin | Employee Portal | Employee Profile | 100% | Working | Completed | - | - | Malar Mam
8 | Kavin | Employee Portal | Employee Layout | 100% | Working | Completed | - | - | Malar Mam
9 | Vinay | Document Management | Document Upload & Verification | 100% | Working | Completed | - | - | Malar Mam
10 | Vinay | Employee Management | Add Employee | 100% | Working | Completed | - | - | Malar Mam
11 | Kavin | Employee Management | Employee List | 100% | Working | Completed | - | - | Malar Mam
12 | Kavin | Employee Management | Employee Profile Review | 100% | Working | Completed | - | - | Malar Mam
13 | Kavin | Communication | Email Communication | 100% | Working | Completed | - | - | Malar Mam
14 | Kavin | Communication | Mail History & Details | 100% | Working | Completed | - | - | Malar Mam
15 | Vinay | Worker Management | Add Worker | 100% | Working | Completed | - | - | Malar Mam
16 | Kavin | Worker Management | Workers Directory | 100% | Working | Completed | - | - | Malar Mam
17 | Kavin | Worker Management | Worker Offer Letter | 100% | Working | Completed | - | - | Malar Mam
18 | Kavin | Admin Dashboard | Sidebar | 100% | Working | Completed | - | - | Malar Mam
19 | Kavin | Admin Dashboard | Topbar & Notifications | 100% | Working | Completed | - | - | Malar Mam
20 | Kavin | Admin Dashboard | Dashboard Analytics | 100% | Working | Completed | - | - | Malar Mam
21 | Vinay | Database | Local SQL Server | 100% | Connected Successfully | In Progress | SQL Server Cloud Hosting | Hosting Pending
22 | Kavin | UI/UX | Frontend CSS for All Pages | 100% | Completed | Completed | - | -
23 | Vinay and Kavin | Testing | System Testing | 80% | Ongoing | In Progress | - | Complete Testing
24 |  | Deployment | Production Deployment | 0% | Not Started | Pending | Production Release | Deployment Pending